## Instructions
Gate Definition & Timeline Pack for PIC
Sumber | Disusun dari file gate_go_no_go_cards (3).html yang diunggah user pada 2026-04-20.
Tujuan workbook | Untuk dibagikan ke PIC agar mereka melengkapi definisi, evidence, status gate, dan update timeline per project.
Bobot gate | Gate 1 = 25%, Gate 2 = 30%, Gate 3 = 25%, Gate 4 = 20%.
Hard gate | Gate 1 dan Gate 3 adalah hard gate. Jika gagal, project tidak layak lanjut meskipun gate lain baik.
Cara pakai | Isi progres aktual hanya di Timeline_Tasks (PIC Start Date dan PIC Actual % Input). Timeline_Periods dan Progress % project akan roll-up otomatis.
Ringkasan Workbook
Total project | 6
Total gate | 499
Total hard gate | 6
Total timeline task | 999
Dropdown reference
Gate status (PIC) | Pass,Conditional,Fail,Not Started
Timeline progress input | Gunakan PIC Actual % Input pada Timeline_Tasks. Tidak lagi memakai status task sebagai penggerak progres.
Reviewer status | Open,In Review,Closed
Panduan Definisi Kolom
Kolom / Istilah | Arti / definisi | Cara isi / contoh | Berlaku di sheet
Hard Gate | Gate kritikal. Jika statusnya Fail, proyek secara prinsip tidak boleh lanjut walaupun gate lain baik. | Di file ini: Gate 1 dan Gate 3 adalah hard gate. | Gate_Definitions
Metric Type | Jenis metric untuk evaluasi. "range" berarti nilai numerik, "select" berarti pilihan status. | range = 92%; select = Pass / Conditional / Fail. | Gate_Metrics
Direction | Arah penilaian metric. "high" berarti makin besar makin baik, "low" berarti makin kecil makin baik. | Precision biasanya high; latency biasanya low. | Gate_Metrics
Current Value | Nilai aktual metric saat ini dari hasil pilot, pengujian, atau implementasi lapangan. | Contoh: uptime 99.1, latency 165, ROI 183. | Gate_Metrics
Pass Threshold | Ambang minimum agar metric dinilai Pass. | Jika direction=high, nilai aktual harus sama atau lebih tinggi dari angka ini. Jika direction=low, nilai aktual harus sama atau lebih rendah dari angka ini. | Gate_Metrics
Conditional Threshold | Ambang tengah untuk status Conditional bila belum mencapai Pass tetapi masih dapat diterima sementara dengan tindak lanjut. | Biasanya dipakai sebagai status warning / perlu improvement. | Gate_Metrics
Min | Batas bawah rentang input untuk metric numerik. | Contoh: 0, 50, atau -100 sesuai karakter metric. | Gate_Metrics
Max | Batas atas rentang input untuk metric numerik. | Contoh: 100 untuk persen, 400 untuk latency, 300 untuk net saving. | Gate_Metrics
Step | Interval kenaikan/perubahan nilai input untuk metric bertipe range. | step 1 = berubah per 1; step 0.1 = berubah per 0,1; step 5 = berubah per 5. | Gate_Metrics
PIC Status | Status penilaian atau update yang diisi PIC. | Gunakan opsi yang sudah disiapkan seperti Pass / Conditional / Fail / Not Started. | Gate_Definitions; Timeline sheets
Reviewer Status | Status review dari evaluator/reviewer setelah PIC mengisi update. | Open / In Review / Closed. | Gate_Definitions; Timeline_Periods
Current Period | Periode aktif project saat ini secara umum. | Contoh: Apr–Jul 2026. | Project_Summary; Timeline_Periods
Roadmap Period | Periode spesifik dalam roadmap project yang berisi fase dan task tertentu. | Contoh: Jan–Mar 2026 atau Apr–Aug 2026. | Timeline_Periods; Timeline_Tasks
Target Date | Tanggal target penyelesaian action, bukti, atau closure update dari PIC. | Isi dengan tanggal target yang realistis. | Gate_Definitions; Timeline sheets
Evidence Link / Folder | Link folder, dokumen, file bukti, atau referensi evidence pendukung status yang diisi PIC. | Bisa berupa Google Drive folder, dokumen test, minutes, screenshot, atau evidence lain. | Gate_Definitions; Gate_Metrics; Timeline_Tasks
Panduan pengisian kolom kuning
Sheet | Kolom kuning yang diisi PIC | Tujuan | Catatan
Gate_Definitions | PIC Status; PIC Notes / Key Findings; Evidence Link / Folder; PIC Owner; Target Close Date; Reviewer Status | Mengisi hasil evaluasi per gate pada level narasi / governance. | Gunakan untuk menjelaskan status gate secara ringkas namun jelas.
Gate_Metrics | PIC Current Finding; PIC Evidence / Source; PIC Comment; Metric Status | Mengisi kondisi aktual tiap metric dan bukti pendukungnya. | Metric Status sebaiknya konsisten dengan nilai aktual vs threshold.
Timeline_Periods | PIC Update Summary; PIC Risks / Dependencies; PIC Owner; Target Date; Reviewer Status | Mengisi narasi kemajuan per phase/periode. Progress % terhitung otomatis dari Timeline_Tasks. | Jangan input progress manual di sini.
Timeline_Tasks | PIC Actual Owner; PIC Start Date; PIC Actual % Input; PIC Progress Note; Evidence Link; Target Date; Dependency / Blocker | Satu-satunya input progres numerik. Nilai ini yang menggerakkan progress phase/period/project. | Isi 0-100 atau 0%-100%; workbook akan normalisasi otomatis.
Catatan: step hanya relevan untuk metric_type = range. Untuk metric_type = select, cukup gunakan pilihan status seperti Pass / Conditional / Fail.
Update workbook | Ditambahkan kolom Need Support (PIC) pada Project_Summary, dropdown untuk Metric Type / Direction / Critical / Unit pada Gate_Metrics, dan sheet khusus untuk setiap project.
Cara pakai sheet per project | Setiap project sekarang memiliki 1 sheet sendiri untuk dibagikan ke PIC. Sheet gabungan tetap dipertahankan sebagai database all project / consolidated view.
Dropdown Metric Type | Pilihan: range, select. Gunakan range untuk angka/continuous metric, dan select untuk pass/conditional/fail.
Dropdown Direction | Pilihan: high, low. high = makin tinggi makin baik; low = makin rendah makin baik. Boleh dikosongkan jika Metric Type = select.
Dropdown Critical | Pilihan: Yes, No. Yes berarti metric kritikal dan biasanya memengaruhi keputusan gate secara langsung.
Dropdown Unit | Pilihan: %, ms, min, pts, /hr, M IDR, mo. Boleh dikosongkan jika Metric Type = select.
Update layout | Pada tiap sheet project, tabel Gate Definitions, Gate Metrics, Timeline Periods, dan Timeline Tasks diposisikan ke kanan (side-by-side) agar PIC bisa menambah row tanpa menabrak section di bawahnya.
Dropdown tambahan | Dropdown tersedia untuk PIC Status, Reviewer Status, Timeline Status, Metric Type, Direction, Critical, dan Unit. Dropdown diterapkan sampai row 2000 pada database gabungan.
Dependency timeline | Progress tidak lagi dipetakan dari status. Roll-up timeline hanya berasal dari PIC Actual % Input pada Timeline_Tasks.
Roll-up period & project | Period Progress % dihitung sebagai rata-rata Task Progress % (normalized) untuk kombinasi Project + Roadmap Period + Phase. Progress % project dihitung sebagai rata-rata Period Progress % per project.
Input utama baru | Timeline_Tasks!I (PIC Actual % Input) menerima angka 0-100 atau format persen. Timeline_Tasks!N menormalkan nilai menjadi persen 0%-100% untuk formula roll-up.
Status period | Period Status sekarang otomatis: Done jika 100%, Progress jika >0%, Plan jika 0%.
NEW LOGIC: Database sheets auto-generate from project sheets
Isi data hanya pada sheet masing-masing project.
Sheet Project_Summary, Gate_Definitions, Gate_Metrics, Timeline_Periods, dan Timeline_Tasks sekarang auto-update dari sheet project.
Jika PIC menambah / mengubah data pada tab project, database gabungan akan ikut berubah otomatis.
Jangan edit sheet database gabungan secara manual karena isinya berasal dari formula reference.

## Project_Summary
Project | Subtitle / Context | Pilot Area | Support Needed | Current Phase | Progress % | Current Period | Next Milestone | Need Support (PIC)
Arcas HD | Heavy automation use case with high dependency on network, ROC monitoring, and safe fallback control. | PAMA BMO2, MTN SMO | kebutuhan akomodasi mesh untuk teknisi yang akan menginap di pama dan mtn awal mei, assist terhadap kebutuhan server dan scurity untuk streaming, tahap awal apakah bisa di fasilitasi maintech. | Pilot proving & controlled expansion | 42.5% | Apr–Jun 2026 | 0 | PAMA dan MTN
MGD PC | Precision-guidance pilot where technical accuracy and field consistency are more critical than raw ROI alone. | PAMA BMO2 | Positioning quality, operator interface, supervised pilot protocol | Accuracy stabilization | 53.33% | Apr–Jun 2026 | Guidance accuracy closeout for broader field test | 0
Remote Pump | Remote operation pilot emphasizing interlock integrity, fail-safe response, and exposure reduction in pump areas. | BC SMO - ACI, BC BMO1 - PMO | 5G / telemetry network, PLC integration, remote command governance | Functional validation & availability proving |  | Apr–Jun 2026 | Interlock sign-off and rollout readiness | 0
Hauling Fleet Management | Optimization pilot where dispatch quality, queue reduction, and utilization improvement drive the business case. | MTL BMO1 | Fleet data pipeline, dispatch integration, performance dashboard | Optimization scaling |  | Apr–Jun 2026 | Portfolio-scale dispatch recommendation | 0
Mining Eyes Analytics | AI surveillance and analytics pilot where assurance value can be as important as direct cash ROI. | PAMA BMO2, PAMA GMO, MTN SMO | 5G infrastructure, cloud, surveillance dashboard (HRZ) | Coverage improvement & workflow hardening |  | Apr–Jun 2026 | False positive reduction and closure workflow maturity | 0
Remote Dozer | Remote dozer pilot with strong linkage between technical readiness, safe remote operation, and direct economical value from fuel and efficiency improvement. | Kalimantan OB Disposal | 5G network, remote control station, video telemetry, autonomous zone & dashboard | Integrated readiness and economic proving | 75% | Apr–Jun 2026 | Technical + economic pack for scale-up decision | 0
Note on A1: Source: gate_go_no_go_cards (3).html (uploaded file)

## Gate_Definitions
Project | Gate | Gate Title | Hard Gate | Gate Definition | Project-specific Explanation | What This Gate Confirms | What PIC Needs to Fill | Original Caption | PIC Status | PIC Notes / Key Findings | Evidence Link / Folder | PIC Owner | Target Close Date | Reviewer Status
Arcas HD | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Arcas HD, gate ini fokus pada network readiness, stability, and end-to-end integration. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Network readiness, stability, and end-to-end integration. | #REF! | Kamera front/disposal berfungsi baik (siang/malam). Frekuensi LiDAR tidak stabil (debu & gangguan grounding). Uji coba menggunakan asumsi jarak 6.4m. Menunggu perbaikan power & grounding di WS. | https://canva.link/59bd8vwqnm3t9r4 | pak ridho | juni week 1 | in review
Arcas HD | Gate 2 | Performance / Effectiveness | Yes | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Arcas HD, gate ini fokus pada accuracy, intervention quality, and stability across shifts. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Accuracy, intervention quality, and stability across shifts. | #REF! | Model YOLO 11 terbukti jauh lebih baik dan responsif dari YOLO 8, meskipun terdapat FPS delay 1 detik dari respon real-time. Alarm berbunyi sesuai limiter target. | https://canva.link/59bd8vwqnm3t9r4 | pak ridho | juni week 1 | in review
Arcas HD | Gate 3 | Safety Case & Procedure | No | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Arcas HD, gate ini fokus pada emergency stop, override, sop, handover, and drill readiness. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Emergency stop, override, SOP, handover, and drill readiness. | #REF! | Sistem peringatan valid direspon oleh operator HD. Tahap selanjutnya akan fokus pada pengujian pengereman otomatis (brake) setelah unit keluar dari WS. | https://canva.link/59bd8vwqnm3t9r4 | pak ridho | juni week 1 | open
Arcas HD | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Arcas HD, gate ini fokus pada exposure reduction, downtime prevention, and scale rationale. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Exposure reduction, downtime prevention, and scale rationale. | #REF! | Belum dapat dievaluasi. Menunggu full system (termasuk brake) selesai terintegrasi | https://canva.link/59bd8vwqnm3t9r4 | pak ridho | juni week 4 | open
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek MGD PC, gate ini fokus pada sensor reliability, positioning accuracy, and data logging. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Sensor reliability, positioning accuracy, and data logging. | Conditional | 0 | 0 | 0 | 0 | 0
MGD PC | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek MGD PC, gate ini fokus pada guidance accuracy, error reduction, and operational acceptance. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Guidance accuracy, error reduction, and operational acceptance. | Conditional | 0 | 0 | 0 | 0 | 0
MGD PC | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek MGD PC, gate ini fokus pada manual fallback, override logic, and safe exception handling. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Manual fallback, override logic, and safe exception handling. | Not Started | 0 | 0 | 0 | 0 | 0
MGD PC | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek MGD PC, gate ini fokus pada operational efficiency, waste reduction, and quality improvement. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Operational efficiency, waste reduction, and quality improvement. | Conditional | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Remote Pump, gate ini fokus pada command success, telemetry completeness, and communication stability. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Command success, telemetry completeness, and communication stability. | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Remote Pump, gate ini fokus pada availability, remote-control reliability, and downtime impact. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Availability, remote-control reliability, and downtime impact. | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Remote Pump, gate ini fokus pada interlock, local override, fail-safe loss-of-signal logic. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Interlock, local override, fail-safe loss-of-signal logic. | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Remote Pump, gate ini fokus pada travel exposure reduction, avoided delays, and operating value. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Travel exposure reduction, avoided delays, and operating value. | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Hauling Fleet Management, gate ini fokus pada data ingestion, gps continuity, dashboard uptime, and integration. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Data ingestion, GPS continuity, dashboard uptime, and integration. | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Hauling Fleet Management, gate ini fokus pada queue time, idle time, and cycle optimization effectiveness. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Queue time, idle time, and cycle optimization effectiveness. | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Hauling Fleet Management, gate ini fokus pada override, rule compliance, and alignment with road safety logic. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Override, rule compliance, and alignment with road safety logic. | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Hauling Fleet Management, gate ini fokus pada fuel efficiency, utilization, and dispatch-led value creation. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Fuel efficiency, utilization, and dispatch-led value creation. | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Mining Eyes Analytics, gate ini fokus pada camera uptime, inference flow, bandwidth, and stream stability. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Camera uptime, inference flow, bandwidth, and stream stability. | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Mining Eyes Analytics, gate ini fokus pada precision, recall, alert usefulness, and missed-event reduction. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Precision, recall, alert usefulness, and missed-event reduction. | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Mining Eyes Analytics, gate ini fokus pada alert escalation, role clarity, verification workflow, and evidence retention. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Alert escalation, role clarity, verification workflow, and evidence retention. | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Mining Eyes Analytics, gate ini fokus pada monitoring coverage, assurance value, and reduction of missed critical events. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Monitoring coverage, assurance value, and reduction of missed critical events. | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Remote Dozer, gate ini fokus pada network readiness, command latency, and telemetry stability for remote dozing. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Network readiness, command latency, and telemetry stability for remote dozing. | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Remote Dozer, gate ini fokus pada distance reduction, remote availability, and fuel-saving effectiveness. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Distance reduction, remote availability, and fuel-saving effectiveness. | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Remote Dozer, gate ini fokus pada emergency stop, fail-safe logic, zone control, and remote handover readiness. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Emergency stop, fail-safe logic, zone control, and remote handover readiness. | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | Gate 4 | Business / Economical Pass | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Remote Dozer, gate ini fokus pada net saving, payback, and long-term roi from remote dozer deployment. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Net saving, payback, and long-term ROI from remote dozer deployment. | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on J1: Kolom kuning diisi PIC.

## Gate_Metrics
Project | Gate | Gate Title | Metric Name | Metric Description | Metric Type | Direction | Critical | Unit | Current Value | Pass Threshold | Conditional Threshold | Min | Max | Step | PIC Current Finding | PIC Evidence / Source | PIC Comment | Metric Status
Arcas HD | Gate 1 | Technical Feasibility | Instalasi power & converter 12V - Setup jaringan (router/modem) - Uji koneksi remote Uji koneksi tanpa streaming Uji remote basic control | Network uptime stabil Packet loss rendah Respons koneksi | system | high | No | % | 95 | 98 | 96 | 90 | 100 | 5 | Sistem jaringan sudah berjalan stabil, belum dilakukan uji streaming penuh (RTSP), Pengujian koneksi awal + catatan belum ada streaming (notulen) | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Kendala bukan pada jaringan, tetapi pada sensor LiDAR dan power unit | pass
Arcas HD | Gate 1 | Technical Feasibility | Testing YOLO lokal (tanpa streaming) - Testing RTSP streaming Uji VLC / RTSP push | Round-trip response delay during operation dan Mampu mendeteksi tanggulan dan air dalam conf 0.8 rata rata | deteksi | low | Yes | ms | 165 | 200 | 250 | 50 | 400 | 5 | delay hanya terjadi pada arcas 1.0 di pama ketika memakai yolo 11 ada delay 1 detik , pengujian di streaming melalui vlc dengan rtsp push mediamtx hasil streaming ada delay 2 detik | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Walaupun ada delay 1 detik, model YOLO 11 dievaluasi jauh lebih baik dan responsif dibanding model YOLO 8. | Conditional
Arcas HD | Gate 1 | Technical Feasibility | Setup logging system - Monitoring koneksi end-to-end, Logging error & event | Status monitoring aktif 100% node terbaca Data tersimpan = Tidak ada loss log >5% | select | high | Yes | `% | 60 | 100 | 60 | 50 | 100 | 1 | Sistem monitoring dan integrasi berjalan normal hanya saya belum bisa terkoneksi dengan power unit karena kendala grounding | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Menunggu jadwal unit ditarik ke Workshop (WS) untuk instalasi sistem pengereman dan perbaikan grounding. | Need Check
Arcas HD | Gate 2 | Performance / Effectiveness | Precision | Akurasi deteksi ≥ 90% Noise detection < 10% | range | high | No | % | 80 | 90 | 80 | 50 | 100 | 1 | secara performa cukup andal meskipun masih ada sedikit noise positive detection, sedangkan lidar masih terganggu masalah sinyal akibat power unit | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Pengujian dilakukan dan tervalidasi langsung melalui respon operator HD di area front dan disposal. | Pass
Arcas HD | Gate 2 | Performance / Effectiveness | Recall | Stabilitas sensor = Tidak ada spike noise Coverage deteksi ≥ 85% Range efektif ≥ 6 meter stabil | system | high | No | % | 80 | 90 | 80 | 50 | 100 | 1 | Sistem dapat mengenali objek sasaran, namun kalkulasi jarak terpaksa dibatasi/diasumsikan di angka 6.4 meter. | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Debu yang sangat tebal mengganggu kestabilan frekuensi Lidar, sehingga cakupan deteksi (recall) belum maksimal. | Conditional
Arcas HD | Gate 3 | Safety Case & Procedure | SOP readiness | Procedure and handover governance completion. | select | 0 | Yes | 0 | Conditional | 0 | 0 | 0 | 0 | 0 | Penulisan draf SOP akan dilakukan setelah perbaikan di WS selesai secara komprehensif. | 0 | Penulisan draf SOP akan dilakukan setelah perbaikan di WS selesai secara komprehensif. | Not Started
Arcas HD | Gate 3 | Safety Case & Procedure | Field drill | Simulation and field drill outcome. | select | 0 | Yes | 0 | Conditional | 0 | 0 | 0 | 0 | 0 | Uji coba pengambilalihan darurat (emergency manual override) belum bisa dieksekusi. | 0 | Menunggu jadwal perbaikan unit di workshop (WS) untuk integrasi brake system ke unit HD. | Not Started
Arcas HD | Gate 4 | Business / Assurance | Exposure reduction | Index of direct exposure removal from hazard zone. | range | high | No | pts | 85 | 80 | 60 | 0 | 100 | 1 | Kalkulasi nilai aktual pengurangan risiko (risk reduction value) belum dapat dihitung secara valid. | 0 | Evaluasi bisnis baru akan dilakukan setelah operasional multi-shift berjalan tanpa intervensi. | Not Started
Arcas HD | Gate 4 | Business / Assurance | Business case quality | Overall economic and assurance justification. | select | 0 | No | 0 | Conditional | 0 | 0 | 0 | 0 | 0 | Rekomendasi ekspansi skala penerapan (roll-out) ke unit lain belum dapat diputuskan. | 0 | Fokus saat ini masih menyelesaikan fase pembuktian teknis dan keamanan (Pilot Area) di PAMA BMO2 dan MTN | Not Started
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | Gate 1 | Technical Feasibility | Position stability | Stability of location/guidance reference. | range | high | No | % | 96 | 95 | 90 | 70 | 100 | 1 | 0 | 0 | 0 | 0
MGD PC | Gate 1 | Technical Feasibility | Data completeness | Availability of pilot evidence for analysis. | range | high | No | % | 95 | 95 | 90 | 70 | 100 | 1 | 0 | 0 | 0 | 0
MGD PC | Gate 1 | Technical Feasibility | System uptime | Application and field support uptime. | range | high | Yes | % | 97.4 | 97 | 95 | 80 | 100 | 0.1 | 0 | 0 | 0 | 0
MGD PC | Gate 2 | Performance / Effectiveness | Guidance accuracy | Accuracy of field guidance versus target. | range | high | No | % | 86 | 90 | 85 | 60 | 100 | 1 | 0 | 0 | 0 | 0
MGD PC | Gate 2 | Performance / Effectiveness | Rework reduction | Reduction in repeated work or adjustment. | range | high | No | % | 6 | 8 | 4 | 0 | 20 | 1 | 0 | 0 | 0 | 0
MGD PC | Gate 2 | Performance / Effectiveness | User acceptance | Supervisor/operator willingness to use the solution. | range | high | No | % | 72 | 80 | 70 | 0 | 100 | 1 | 0 | 0 | 0 | 0
MGD PC | Gate 3 | Safety Case & Procedure | Override readiness | Manual fallback and override usability. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | Gate 3 | Safety Case & Procedure | Pilot SOP | Approved procedure for assisted/manual operation. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | Gate 3 | Safety Case & Procedure | Critical risk closure | Closure of open major safety issues. | range | high | Yes | % | 100 | 100 | 90 | 0 | 100 | 1 | 0 | 0 | 0 | 0
MGD PC | Gate 4 | Business / Assurance | Cycle benefit | Cycle improvement from assisted guidance. | range | high | No | % | 6 | 8 | 5 | 0 | 20 | 1 | 0 | 0 | 0 | 0
MGD PC | Gate 4 | Business / Assurance | Waste / rework gain | Reduction in avoidable quality loss. | range | high | No | % | 5 | 7 | 4 | 0 | 20 | 1 | 0 | 0 | 0 | 0
MGD PC | Gate 4 | Business / Assurance | Scale rationale | Readiness to move beyond proof-of-concept stage. | select | 0 | No | 0 | conditional | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | Gate 1 | Technical Feasibility | Command success rate | Success of issued remote command. | range | high | Yes | % | 98.8 | 98 | 95 | 80 | 100 | 0.1 | 0 | 0 | 0 | 0
Remote Pump | Gate 1 | Technical Feasibility | Telemetry completeness | Availability of remote feedback and audit data. | range | high | No | % | 97 | 95 | 90 | 70 | 100 | 1 | 0 | 0 | 0 | 0
Remote Pump | Gate 1 | Technical Feasibility | Communication uptime | Reliability of communication channel. | range | high | Yes | % | 99 | 98 | 96 | 80 | 100 | 0.1 | 0 | 0 | 0 | 0
Remote Pump | Gate 2 | Performance / Effectiveness | Remote availability | Ability to operate remotely when needed. | range | high | No | % | 91 | 90 | 85 | 50 | 100 | 1 | 0 | 0 | 0 | 0
Remote Pump | Gate 2 | Performance / Effectiveness | Response latency | Control response time under operating condition. | range | low | No | ms | 180 | 200 | 250 | 50 | 400 | 5 | 0 | 0 | 0 | 0
Remote Pump | Gate 2 | Performance / Effectiveness | Downtime reduction | Reduction in event-driven downtime. | range | high | No | % | 11 | 10 | 5 | 0 | 30 | 1 | 0 | 0 | 0 | 0
Remote Pump | Gate 3 | Safety Case & Procedure | Safety interlock | Integrity of remote command permissive chain. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | Gate 3 | Safety Case & Procedure | Loss-of-signal fail-safe | Safe fallback when signal is lost. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | Gate 3 | Safety Case & Procedure | Isolation procedure | LOTO and local takeover procedure readiness. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | Gate 4 | Business / Assurance | Travel exposure reduction | Reduction in personnel movement to pump area. | range | high | No | % | 18 | 15 | 8 | 0 | 40 | 1 | 0 | 0 | 0 | 0
Remote Pump | Gate 4 | Business / Assurance | Delay prevention | Avoided delay from remote intervention. | range | high | No | % | 11 | 10 | 5 | 0 | 20 | 1 | 0 | 0 | 0 | 0
Remote Pump | Gate 4 | Business / Assurance | Economic case | Scale case from avoided loss and assurance benefit. | select | 0 | No | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 1 | Technical Feasibility | Data ingestion | Consistency of live fleet data ingestion. | range | high | No | % | 97 | 95 | 90 | 70 | 100 | 1 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 1 | Technical Feasibility | Dashboard uptime | Operational dashboard availability. | range | high | Yes | % | 99.2 | 98 | 96 | 80 | 100 | 0.1 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 1 | Technical Feasibility | Refresh cycle | Minutes needed for usable data refresh. | range | low | No | min | 5 | 10 | 20 | 1 | 60 | 1 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 2 | Performance / Effectiveness | Queue time reduction | Reduction in waiting queue for loading/unloading. | range | high | No | % | 14 | 10 | 5 | 0 | 30 | 1 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 2 | Performance / Effectiveness | Idle reduction | Reduction in idle or non-productive unit time. | range | high | No | % | 10 | 8 | 4 | 0 | 20 | 1 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 2 | Performance / Effectiveness | User adoption | Dispatcher and supervisor usage level. | range | high | No | % | 89 | 85 | 75 | 0 | 100 | 1 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 3 | Safety Case & Procedure | Safety conflict check | No contradiction with road-rule protections. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 3 | Safety Case & Procedure | Audit trail | Decision traceability and reviewability. | select | 0 | No | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 3 | Safety Case & Procedure | Escalation path | Manual override and escalation remain available. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 4 | Business / Assurance | Fuel benefit | Improvement in fuel-related operating value. | range | high | No | % | 6 | 5 | 2 | 0 | 15 | 1 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 4 | Business / Assurance | Utilization uplift | Increase in productive fleet use. | range | high | No | % | 9 | 7 | 4 | 0 | 20 | 1 | 0 | 0 | 0 | 0
Hauling Fleet Management | Gate 4 | Business / Assurance | Scale economics | Strength of economic case for wider deployment. | select | 0 | No | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 1 | Technical Feasibility | Camera uptime | Video source availability for analytics. | range | high | No | % | 96.5 | 97 | 95 | 70 | 100 | 0.1 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 1 | Technical Feasibility | Inference latency | Speed from event to generated alert. | range | low | No | ms | 220 | 250 | 350 | 50 | 700 | 10 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 1 | Technical Feasibility | Coverage stability | Consistency of effective area coverage. | range | high | Yes | % | 82 | 85 | 75 | 0 | 100 | 1 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 2 | Performance / Effectiveness | Precision | Alert correctness rate. | range | high | No | % | 84 | 90 | 80 | 50 | 100 | 1 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 2 | Performance / Effectiveness | Recall | Ability to capture true events. | range | high | No | % | 78 | 85 | 75 | 50 | 100 | 1 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 2 | Performance / Effectiveness | False positive rate | Lower rate reduces alert fatigue. | range | low | No | /hr | 0.45 | 0.25 | 0.45 | 0 | 1 | 0.01 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 3 | Safety Case & Procedure | Escalation SOP | Owner and response flow for incoming alerts. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 3 | Safety Case & Procedure | Audit trail | Evidence trace and alert history reviewability. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 3 | Safety Case & Procedure | Closure workflow | Quality of action closure discipline. | range | high | No | % | 72 | 80 | 70 | 0 | 100 | 1 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 4 | Business / Assurance | Coverage uplift | Increase in monitored area or observation capability. | range | high | No | % | 31 | 25 | 15 | 0 | 50 | 1 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 4 | Business / Assurance | Manual review reduction | Potential reduction in CCTV review effort. | range | high | No | % | 18 | 20 | 10 | 0 | 40 | 1 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Gate 4 | Business / Assurance | Assurance case | Strength of visibility and auditability justification. | select | 0 | No | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | Gate 1 | Technical Feasibility | Network uptime | Availability of network used for remote dozer control. | range | high | Yes | % | 99 | 98 | 96 | 80 | 100 | 0.1 | 0 | 0 | 0 | 0
Remote Dozer | Gate 1 | Technical Feasibility | Control latency | Round-trip command latency during remote operation. | range | low | Yes | ms | 170 | 200 | 250 | 50 | 400 | 5 | 0 | 0 | 0 | 0
Remote Dozer | Gate 2 | Performance / Effectiveness | Dozing distance reduction | Reduction in average push distance versus conventional operation. | range | high | No | % | 75 | 60 | 40 | 0 | 100 | 1 | 0 | 0 | 0 | 0
Remote Dozer | Gate 2 | Performance / Effectiveness | Remote operating availability | Percentage of planned operating time executed in remote mode. | range | high | No | % | 91 | 85 | 75 | 40 | 100 | 1 | 0 | 0 | 0 | 0
Remote Dozer | Gate 3 | Safety Case & Procedure | Emergency stop readiness | Remote and local emergency stop function. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | Gate 3 | Safety Case & Procedure | Loss-of-signal fail-safe | Machine response when communication is interrupted. | select | 0 | Yes | 0 | pass | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | Gate 4 | Business / Economical Pass | Net saving / month | Monthly net saving after fuel saving and maintenance impact. | range | high | No | M IDR | 165 | 100 | 40 | -100 | 300 | 1 | 0 | 0 | 0 | 0
Remote Dozer | Gate 4 | Business / Economical Pass | Simple payback | Capital recovery period. Lower is better. | range | low | No | mo | 21 | 36 | 60 | 1 | 120 | 1 | 0 | 0 | 0 | 0
Remote Dozer | Gate 4 | Business / Economical Pass | 5-year ROI | Return on investment over five years after CAPEX recovery. | range | high | No | % | 183 | 50 | 0 | -100 | 400 | 1 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Timeline_Periods
Project | Current Period | Roadmap Period | Phase | Period Status | Period Explanation | Planned Objective / Outcome | PIC Update Summary | PIC Risks / Dependencies | PIC Owner | Target Date | Reviewer Status | Period Progress %
Arcas HD | Apr - Jun 2026 | Jan - Mar 2026 | Infrastructure & technical proving | Progress | Fase Infrastructure & technical proving pada periode Jan–Mar 2026 untuk Arcas HD. | Validate network backbone and ROC connection stability; Complete initial end-to-end system integration test | Infrastruktur RTK dan server VPS monitoring sudah siap beroperasi 24/7. Evaluasi visual kamera siang dan malam di area tambang berjalan lancar. | 0 | masbukhin | 46112 | on review | 60%
Arcas HD | Apr - Jun 2026 | Apr - Jun 2026 | Pilot operation & safety proving | Progress | Fase Pilot operation & safety proving pada periode Apr–Jun 2026 untuk Arcas HD. | Run supervised multi-shift pilot scenario; Prepare Gate 3 evidence pack for approval | Perakitan box kontrol, pemasangan wiring, dan instalasi bracket sensor pada unit HD selesai dilakukan. | 0 | masbukhin | 46142 | open | 25%
Arcas HD | Apr - Jun 2026 | Jul- Sept 2026 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | Apr - Jun 2026 | Oct - Dec 2026 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Arcas HD | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | Apr - Jun 2026 | Jan–Mar 2026 | Configuration & setup | Progress | Fase Configuration & setup pada periode Jan–Feb 2026 untuk MGD PC. | Install positioning and guidance configuration; Validate data logging and field test protocol; Train pilot supervisors on assisted workflow | 0 | 0 | 0 | 0 | 0 | 73.33%
MGD PC | Apr - Jun 2026 | Jan–Mar 2026 | Pilot proving | Progress | Fase Pilot proving pada periode Mar–Jun 2026 untuk MGD PC. | Improve guidance accuracy at variable work fronts; Monitor user adoption and coaching needs; Review rework reduction evidence by shift | 0 | 0 | 0 | 0 | 0 | 33.33%
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
MGD PC | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | Apr - Jun 2026 | Jan - Mar 2026 | Remote control commissioning |  | Fase Remote control commissioning pada periode Jan–Mar 2026 untuk Remote Pump. | Commission telemetry and command loop; Validate remote signal reliability; Prepare pump isolation and takeover workflow | 0 | 0 | 0 | 0 | 0
Remote Pump | Apr - Jun 2026 | Jan - Mar 2026 | Operational pilot and fail-safe proving |  | Fase Operational pilot and fail-safe proving pada periode Apr–Jul 2026 untuk Remote Pump. | Complete fail-safe loss-of-signal scenarios; Track downtime reduction against baseline; Document local override discipline by area | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Pump | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Apr - Jun 2026 | Jan–Mar 2026 | Data and dashboard stabilization |  | Fase Data and dashboard stabilization pada periode Jan–Mar 2026 untuk Hauling Fleet Management. | Stabilize fleet data ingestion pipeline; Launch dispatcher dashboard and KPI baseline; Validate refresh cycle for operational use | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | Apr - Jun 2026 | Jan–Mar 2026 | Optimization proving |  | Fase Optimization proving pada periode Apr–Aug 2026 untuk Hauling Fleet Management. | Track queue and idle reduction by shift; Improve user adoption across supervisors; Lock fuel and utilization uplift evidence | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hauling Fleet Management | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Apr - Jun 2026 | Jan–Mar 2026 | Camera and analytics setup |  | Fase Camera and analytics setup pada periode Jan–Mar 2026 untuk Mining Eyes Analytics. | Deploy camera integration and basic inference flow; Stand up surveillance dashboard and alert feed; Define escalation owners and verification workflow | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | Apr - Jun 2026 | Jan–Mar 2026 | Model and workflow improvement |  | Fase Model and workflow improvement pada periode Apr–Jul 2026 untuk Mining Eyes Analytics. | Reduce false positives at priority use cases; Improve closure discipline and evidence linkage; Strengthen coverage in unstable network areas | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mining Eyes Analytics | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | Apr - Jun 2026 | Jan - Mar 2026 | Remote system setup | Done | Fase Remote system setup pada periode Jan–Mar 2026 untuk Remote Dozer. | Complete network and control station setup; Define remote zone boundary and procedure | 0 | 0 | 0 | 0 | 0 | 100%
Remote Dozer | Apr - Jun 2026 | Apr - Jun 2026 | Pilot run and economic proof | Progress | Fase Pilot run and economic proof pada periode Apr–Aug 2026 untuk Remote Dozer. | Track dozing distance reduction and remote availability; Refresh payback and ROI assumption model | 0 | 0 | 0 | 0 | 0 | 50%
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Remote Dozer | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Timeline_Tasks
Project | Roadmap Period | Phase | Task | Original Owner | Original Status | PIC Actual Owner | PIC Start Date | PIC Actual % Input | PIC Progress Note | Evidence Link | Target Date | Dependency / Blocker | Task Progress % (Normalized)
Arcas HD | Jan - Mar 2026 | Infrastructure & technical proving | Validate network backbone and ROC connection stability | IT / Automation | Done | Poltek | 2026-03-25 | 1 | Infrastruktur jaringan, RTK, dan server VPS (MediaMTX) telah siap beroperasi. Perakitan kontrol box, wiring, dan integrasi kamera ke unit HD selesai 100%. | https://canva.link/59bd8vwqnm3t9r4 | 0 | belum dilakukan pengujian secara terus menerus 1 minggu dan belum bisa dilihat hasil validasi totalnya kendalanya karena masih menggunakan power external karena masalah sinyal frekuensi power unit, untuk di mtn progres dalam keseluruhan assembly belum dilakukan percobaan langsung | 60`%
Arcas HD | Jan - Mar 2026 | Infrastructure & technical proving | Complete initial end-to-end system integration test | Vendor + Ops | Done | Poltek | 2026-04-20 | 1 | Uji coba di front & disposal berjalan baik menggunakan YOLO 11 (akurasi tinggi meski delay 1 detik). Alarm sinkron dengan deteksi visual. Pengujian LiDAR menggunakan asumsi jarak 6.4m. | https://canva.link/59bd8vwqnm3t9r5 | 0 | integrasi hanya terkendali pada integrasi power unit bottle necknya adalah dengan mengganti sistem grounding sensor tidak dijadikan satu dengan power utama mengambil power dari grounding kontrol | 60%
Arcas HD | Apr - Jun 2026 | Pilot operation & safety proving | Run supervised multi-shift pilot scenario | Ops | Progress | Poltek | 0 | 0.5 | belum dilakukan | 0 | 46166 | 0% | 50%
Arcas HD | Apr - Jun 2026 | Pilot operation & safety proving | Prepare Gate 3 evidence pack for approval | Project Team | Plan | Poltek | 0 | 0 | belum dilakukan | 0 | 46167 | 0% | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Arcas HD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | Jan–Mar 2026 | Configuration & setup | Install positioning and guidance configuration | Vendor | Done | 0 | 0 | 100 | 0 | 0 | 0 | 0% | 100%
MGD PC | Jan–Mar 2026 | Configuration & setup | Validate data logging and field test protocol | Data Team | Done | 0 | 0 | 20 | 0 | 0 | 0 | 0% | 20%
MGD PC | Jan–Mar 2026 | Configuration & setup | Train pilot supervisors on assisted workflow | Ops | Done | 0 | 0 | 100 | 0 | 0 | 0 | 0% | 100%
MGD PC | Jan–Mar 2026 | Pilot proving | Improve guidance accuracy at variable work fronts | Vendor + Ops | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
MGD PC | Jan–Mar 2026 | Pilot proving | Monitor user adoption and coaching needs | Supervisor | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
MGD PC | Jan–Mar 2026 | Pilot proving | Review rework reduction evidence by shift | Project Analyst | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
MGD PC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | Jan–Mar 2026 | Remote control commissioning | Commission telemetry and command loop | Automation | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Remote Pump | Jan–Mar 2026 | Remote control commissioning | Validate remote signal reliability | IT / Vendor | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Remote Pump | Jan–Mar 2026 | Remote control commissioning | Prepare pump isolation and takeover workflow | Maintenance | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Remote Pump | Apr–Jul 2026 | Operational pilot and fail-safe proving | Complete fail-safe loss-of-signal scenarios | Automation + OHS | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
Remote Pump | Apr–Jul 2026 | Operational pilot and fail-safe proving | Track downtime reduction against baseline | Project Analyst | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
Remote Pump | Apr–Jul 2026 | Operational pilot and fail-safe proving | Document local override discipline by area | Maintenance | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Pump | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | Jan - Mar 2026 | Data and dashboard stabilization | Stabilize fleet data ingestion pipeline | Data Eng | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Hauling Fleet Management | Jan - Mar 2026 | Data and dashboard stabilization | Launch dispatcher dashboard and KPI baseline | Analytics | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Hauling Fleet Management | Jan - Mar 2026 | Data and dashboard stabilization | Validate refresh cycle for operational use | Ops Control | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Hauling Fleet Management | Jan - Mar 2026 | Optimization proving | Track queue and idle reduction by shift | Dispatcher | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
Hauling Fleet Management | Jan - Mar 2026 | Optimization proving | Improve user adoption across supervisors | Ops | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
Hauling Fleet Management | Jan - Mar 2026 | Optimization proving | Lock fuel and utilization uplift evidence | Project Analyst | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Hauling Fleet Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | Jan - Mar 2026 | Camera and analytics setup | Deploy camera integration and basic inference flow | Vendor | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Mining Eyes Analytics | Jan - Mar 2026 | Camera and analytics setup | Stand up surveillance dashboard and alert feed | IT / Analytics | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Mining Eyes Analytics | Jan - Mar 2026 | Camera and analytics setup | Define escalation owners and verification workflow | OHS | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Mining Eyes Analytics | Jan - Mar 2026 | Model and workflow improvement | Reduce false positives at priority use cases | AI Team | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
Mining Eyes Analytics | Jan - Mar 2026 | Model and workflow improvement | Improve closure discipline and evidence linkage | Ops + OHS | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
Mining Eyes Analytics | Jan - Mar 2026 | Model and workflow improvement | Strengthen coverage in unstable network areas | IT | Risk | 0 | 0 | 0.25 | 0 | 0 | 0 | 0% | 25%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Mining Eyes Analytics | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | Jan - Mar 2026 | Remote system setup | Complete network and control station setup | Automation | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Remote Dozer | Jan - Mar 2026 | Remote system setup | Define remote zone boundary and procedure | OHS | Done | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 100%
Remote Dozer | Apr - Jun 2026 | Pilot run and economic proof | Track dozing distance reduction and remote availability | Ops | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
Remote Dozer | Apr - Jun 2026 | Pilot run and economic proof | Refresh payback and ROI assumption model | Project Analyst | Progress | 0 | 0 | 0.5 | 0 | 0 | 0 | 0% | 50%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Remote Dozer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Note on H1: Gunakan dropdown status untuk update task.

## Arcas HD
Arcas HD - PIC Working Sheet
Section ditata ke kanan (side-by-side) agar PIC bebas menambah row per tabel. Input progres hanya di Timeline Tasks (Start Date + Actual %); Period Progress dan Project Progress roll-up otomatis.
Project Summary
Project | Arcas HD |  |  | Pilot Area | PAMA BMO2, MTN SMO
Subtitle / Context | Heavy automation use case with high dependency on network, ROC monitoring, and safe fallback control. |  |  | Support Needed | kebutuhan akomodasi mesh untuk teknisi yang akan menginap di pama dan mtn awal mei, assist terhadap kebutuhan server dan scurity untuk streaming, tahap awal apakah bisa di fasilitasi maintech.
Current Phase | Pilot proving & controlled expansion |  |  | Progress % | 42.5%
Current Period | Apr–Jun 2026 |  |  | Next Milestone
Need Support (PIC) | PAMA dan MTN
Gate Definitions | [14 empty] | Gate Metrics | [18 empty] | Timeline Periods | [12 empty] | Timeline Tasks
Project+A12:K17B9A1A12:I40 | Gate | Gate Title | Hard Gate | Gate Definition | Project-specific Explanation | What This Gate Confirms | What PIC Needs to Fill | Original Caption | PIC Status | PIC Notes / Key Findings | Evidence Link / Folder | PIC Owner | Target Close Date | Reviewer Status | Project | Gate | Gate Title | Metric Name | Metric Description | Metric Type | Direction | Critical | Unit | Current Value | Pass Threshold | Conditional Threshold | Min | Max | Step | PIC Current Finding | PIC Evidence / Source | PIC Comment | Metric Status | Project | Current Period | Roadmap Period | Phase | Period Status | Period Explanation | Planned Objective / Outcome | PIC Update Summary | PIC Risks / Dependencies | PIC Owner | Target Date | Reviewer Status | Period Progress % | Project | Roadmap Period | Phase | Task | Original Owner | Original Status | PIC Actual Owner | PIC Start Date | PIC Actual % Input | PIC Progress Note | Evidence Link | Target Date | Dependency / Blocker | Task Progress % (Normalized)
Arcas HD | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Arcas HD, gate ini fokus pada network readiness, stability, and end-to-end integration. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Network readiness, stability, and end-to-end integration. | Conditional | Kamera front/disposal berfungsi baik (siang/malam). Frekuensi LiDAR tidak stabil (debu & gangguan grounding). Uji coba menggunakan asumsi jarak 6.4m. Menunggu perbaikan power & grounding di WS. | https://canva.link/59bd8vwqnm3t9r4 | pak ridho | juni week 1 | in review | Arcas HD | Gate 1 | Technical Feasibility | Instalasi power & converter 12V - Setup jaringan (router/modem) - Uji koneksi remote Uji koneksi tanpa streaming Uji remote basic control | Network uptime stabil Packet loss rendah Respons koneksi | system | high | No | % | 95 | 98 | 96 | 90 | 100 | 5 | Sistem jaringan sudah berjalan stabil, belum dilakukan uji streaming penuh (RTSP), Pengujian koneksi awal + catatan belum ada streaming (notulen) | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Kendala bukan pada jaringan, tetapi pada sensor LiDAR dan power unit | pass | Arcas HD | Apr - Jun 2026 | Jan - Mar 2026 | Infrastructure & technical proving | Progress | Fase Infrastructure & technical proving pada periode Jan–Mar 2026 untuk Arcas HD. | Validate network backbone and ROC connection stability; Complete initial end-to-end system integration test | Infrastruktur RTK dan server VPS monitoring sudah siap beroperasi 24/7. Evaluasi visual kamera siang dan malam di area tambang berjalan lancar. |  | masbukhin | 2026-03-31 | on review | 60% | Arcas HD | Jan - Mar 2026 | Infrastructure & technical proving | Validate network backbone and ROC connection stability | IT / Automation | Done | Poltek | 2026-03-25 | 1 | Infrastruktur jaringan, RTK, dan server VPS (MediaMTX) telah siap beroperasi. Perakitan kontrol box, wiring, dan integrasi kamera ke unit HD selesai 100%. | https://canva.link/59bd8vwqnm3t9r4 |  | belum dilakukan pengujian secara terus menerus 1 minggu dan belum bisa dilihat hasil validasi totalnya kendalanya karena masih menggunakan power external karena masalah sinyal frekuensi power unit, untuk di mtn progres dalam keseluruhan assembly belum dilakukan percobaan langsung | 60`%
Arcas HD | Gate 2 | Performance / Effectiveness | Yes | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Arcas HD, gate ini fokus pada accuracy, intervention quality, and stability across shifts. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Accuracy, intervention quality, and stability across shifts. | Conditional | Model YOLO 11 terbukti jauh lebih baik dan responsif dari YOLO 8, meskipun terdapat FPS delay 1 detik dari respon real-time. Alarm berbunyi sesuai limiter target. | https://canva.link/59bd8vwqnm3t9r4 | pak ridho | juni week 1 | in review | Arcas HD | Gate 1 | Technical Feasibility | Testing YOLO lokal (tanpa streaming) - Testing RTSP streaming Uji VLC / RTSP push | Round-trip response delay during operation dan Mampu mendeteksi tanggulan dan air dalam conf 0.8 rata rata | deteksi | low | Yes | ms | 165 | 200 | 250 | 50 | 400 | 5 | delay hanya terjadi pada arcas 1.0 di pama ketika memakai yolo 11 ada delay 1 detik , pengujian di streaming melalui vlc dengan rtsp push mediamtx hasil streaming ada delay 2 detik | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Walaupun ada delay 1 detik, model YOLO 11 dievaluasi jauh lebih baik dan responsif dibanding model YOLO 8. | Conditional | Arcas HD | Apr - Jun 2026 | Apr - Jun 2026 | Pilot operation & safety proving | Progress | Fase Pilot operation & safety proving pada periode Apr–Jun 2026 untuk Arcas HD. | Run supervised multi-shift pilot scenario; Prepare Gate 3 evidence pack for approval | Perakitan box kontrol, pemasangan wiring, dan instalasi bracket sensor pada unit HD selesai dilakukan. |  | masbukhin | 2026-04-30 | open | 25% | Arcas HD | Jan - Mar 2026 | Infrastructure & technical proving | Complete initial end-to-end system integration test | Vendor + Ops | Done | Poltek | 2026-04-20 | 1 | Uji coba di front & disposal berjalan baik menggunakan YOLO 11 (akurasi tinggi meski delay 1 detik). Alarm sinkron dengan deteksi visual. Pengujian LiDAR menggunakan asumsi jarak 6.4m. | https://canva.link/59bd8vwqnm3t9r5 |  | integrasi hanya terkendali pada integrasi power unit bottle necknya adalah dengan mengganti sistem grounding sensor tidak dijadikan satu dengan power utama mengambil power dari grounding kontrol | 60%
Arcas HD | Gate 3 | Safety Case & Procedure | No | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Arcas HD, gate ini fokus pada emergency stop, override, sop, handover, and drill readiness. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Emergency stop, override, SOP, handover, and drill readiness. | Not Started | Sistem peringatan valid direspon oleh operator HD. Tahap selanjutnya akan fokus pada pengujian pengereman otomatis (brake) setelah unit keluar dari WS. | https://canva.link/59bd8vwqnm3t9r4 | pak ridho | juni week 1 | open | Arcas HD | Gate 1 | Technical Feasibility | Training / load model YOLO , Testing objek tanggul & air Validasi visual hasil deteksi | Confidence detection ≥ 0.8 rata-rata Deteksi valid ≥ 80% benar (awal) | select | high | Yes | % | 75 | 80 | 75 | 70 | 80 | 2 | Sistem mampu mendeteksi objek (tanggul & air) dengan respon alarm sesuai kondisi, “Alarm berbunyi sesuai kondisi… respon operator HD” | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Validasi sudah dilakukan langsung oleh operator di lapangan | pass | Arcas HD | Apr - Jun 2026 | Jul- Sept 2026 | [10 empty] | Arcas HD | Apr - Jun 2026 | Pilot operation & safety proving | Run supervised multi-shift pilot scenario | Ops | Progress | Poltek |  | 0.5 | belum dilakukan |  | 2026-05-24 |  | 50%
Arcas HD | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Arcas HD, gate ini fokus pada exposure reduction, downtime prevention, and scale rationale. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Exposure reduction, downtime prevention, and scale rationale. | Conditional | Belum dapat dievaluasi. Menunggu full system (termasuk brake) selesai terintegrasi | https://canva.link/59bd8vwqnm3t9r4 | pak ridho | juni week 4 | open | Arcas HD | Gate 1 | Technical Feasibility | Setup logging system - Monitoring koneksi end-to-end, Logging error & event | Status monitoring aktif 100% node terbaca Data tersimpan = Tidak ada loss log >5% | select | high | Yes | `% | 60 | 100 | 60 | 50 | 100 | 1 | Sistem monitoring dan integrasi berjalan normal hanya saya belum bisa terkoneksi dengan power unit karena kendala grounding | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Menunggu jadwal unit ditarik ke Workshop (WS) untuk instalasi sistem pengereman dan perbaikan grounding. | Need Check | Arcas HD | Apr - Jun 2026 | Oct - Dec 2026 | [10 empty] | Arcas HD | Apr - Jun 2026 | Pilot operation & safety proving | Prepare Gate 3 evidence pack for approval | Project Team | Plan | Poltek |  | 0 | belum dilakukan |  | 2026-05-25 |  | 0%
Arcas HD | [14 empty] | Arcas HD | Gate 2 | Performance / Effectiveness | Precision | Akurasi deteksi ≥ 90% Noise detection < 10% | range | high | No | % | 80 | 90 | 80 | 50 | 100 | 1 | secara performa cukup andal meskipun masih ada sedikit noise positive detection, sedangkan lidar masih terganggu masalah sinyal akibat power unit | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Pengujian dilakukan dan tervalidasi langsung melalui respon operator HD di area front dan disposal. | Pass | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | Gate 2 | Performance / Effectiveness | Recall | Stabilitas sensor = Tidak ada spike noise Coverage deteksi ≥ 85% Range efektif ≥ 6 meter stabil | system | high | No | % | 80 | 90 | 80 | 50 | 100 | 1 | Sistem dapat mengenali objek sasaran, namun kalkulasi jarak terpaksa dibatasi/diasumsikan di angka 6.4 meter. | https://docs.google.com/document/d/1MJEyCaIV3R5pvN7PUfL2eEw_2Uv8J7hX/edit?usp=drive_link&ouid=106413634385719121055&rtpof=true&sd=true | Debu yang sangat tebal mengganggu kestabilan frekuensi Lidar, sehingga cakupan deteksi (recall) belum maksimal. | Conditional | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | Gate 3 | Safety Case & Procedure | SOP readiness | Procedure and handover governance completion. | select |  | Yes |  | Conditional | [5 empty] | Penulisan draf SOP akan dilakukan setelah perbaikan di WS selesai secara komprehensif. |  | Penulisan draf SOP akan dilakukan setelah perbaikan di WS selesai secara komprehensif. | Not Started | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | Gate 3 | Safety Case & Procedure | Field drill | Simulation and field drill outcome. | select |  | Yes |  | Conditional | [5 empty] | Uji coba pengambilalihan darurat (emergency manual override) belum bisa dieksekusi. |  | Menunggu jadwal perbaikan unit di workshop (WS) untuk integrasi brake system ke unit HD. | Not Started | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | Gate 4 | Business / Assurance | Exposure reduction | Index of direct exposure removal from hazard zone. | range | high | No | pts | 85 | 80 | 60 | 0 | 100 | 1 | Kalkulasi nilai aktual pengurangan risiko (risk reduction value) belum dapat dihitung secara valid. |  | Evaluasi bisnis baru akan dilakukan setelah operasional multi-shift berjalan tanpa intervensi. | Not Started | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | Gate 4 | Business / Assurance | Business case quality | Overall economic and assurance justification. | select |  | No |  | Conditional | [5 empty] | Rekomendasi ekspansi skala penerapan (roll-out) ke unit lain belum dapat diputuskan. |  | Fokus saat ini masih menyelesaikan fase pembuktian teknis dan keamanan (Pilot Area) di PAMA BMO2 dan MTN | Not Started | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD | [14 empty] | Arcas HD | [18 empty] | Arcas HD | [12 empty] | Arcas HD
Arcas HD

## MGD PC
MGD PC - PIC Working Sheet
Section ditata ke kanan (side-by-side) agar PIC bebas menambah row per tabel. Input progres hanya di Timeline Tasks (Start Date + Actual %); Period Progress dan Project Progress roll-up otomatis.
Project Summary
Project | MGD PC |  |  | Pilot Area | PAMA BMO2
Subtitle / Context | Precision-guidance pilot where technical accuracy and field consistency are more critical than raw ROI alone. |  |  | Support Needed | Positioning quality, operator interface, supervised pilot protocol
Current Phase | Accuracy stabilization |  |  | Progress % | 53.33%
Current Period | Apr–Jun 2026 |  |  | Next Milestone | Guidance accuracy closeout for broader field test
Need Support (PIC)
Gate Definitions | [14 empty] | Gate Metrics | [18 empty] | Timeline Periods | [12 empty] | Timeline Tasks
Project | Gate | Gate Title | Hard Gate | Gate Definition | Project-specific Explanation | What This Gate Confirms | What PIC Needs to Fill | Original Caption | PIC Status | PIC Notes / Key Findings | Evidence Link / Folder | PIC Owner | Target Close Date | Reviewer Status | Project | Gate | Gate Title | Metric Name | Metric Description | Metric Type | Direction | Critical | Unit | Current Value | Pass Threshold | Conditional Threshold | Min | Max | Step | PIC Current Finding | PIC Evidence / Source | PIC Comment | Metric Status | Project | Current Period | Roadmap Period | Phase | Period Status | Period Explanation | Planned Objective / Outcome | PIC Update Summary | PIC Risks / Dependencies | PIC Owner | Target Date | Reviewer Status | Period Progress % | Project | Roadmap Period | Phase | Task | Original Owner | Original Status | PIC Actual Owner | PIC Start Date | PIC Actual % Input | PIC Progress Note | Evidence Link | Target Date | Dependency / Blocker | Task Progress % (Normalized)
MGD PC | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek MGD PC, gate ini fokus pada sensor reliability, positioning accuracy, and data logging. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Sensor reliability, positioning accuracy, and data logging. | [6 empty] | MGD PC | Gate 1 | Technical Feasibility | Position stability | Stability of location/guidance reference. | range | high | No | % | 96 | 95 | 90 | 70 | 100 | 1 |  |  |  |  | MGD PC | Apr - Jun 2026 | Jan–Mar 2026 | Configuration & setup | Progress | Fase Configuration & setup pada periode Jan–Feb 2026 untuk MGD PC. | Install positioning and guidance configuration; Validate data logging and field test protocol; Train pilot supervisors on assisted workflow | [5 empty] | 73.33% | MGD PC | Jan–Mar 2026 | Configuration & setup | Install positioning and guidance configuration | Vendor | Done |  |  | 100 |  |  |  |  | 100%
MGD PC | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek MGD PC, gate ini fokus pada guidance accuracy, error reduction, and operational acceptance. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Guidance accuracy, error reduction, and operational acceptance. | [6 empty] | MGD PC | Gate 1 | Technical Feasibility | Data completeness | Availability of pilot evidence for analysis. | range | high | No | % | 95 | 95 | 90 | 70 | 100 | 1 |  |  |  |  | MGD PC | Apr - Jun 2026 | Jan–Mar 2026 | Pilot proving | Progress | Fase Pilot proving pada periode Mar–Jun 2026 untuk MGD PC. | Improve guidance accuracy at variable work fronts; Monitor user adoption and coaching needs; Review rework reduction evidence by shift | [5 empty] | 33.33% | MGD PC | Jan–Mar 2026 | Configuration & setup | Validate data logging and field test protocol | Data Team | Done |  |  | 20 |  |  |  |  | 20%
MGD PC | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek MGD PC, gate ini fokus pada manual fallback, override logic, and safe exception handling. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Manual fallback, override logic, and safe exception handling. | [6 empty] | MGD PC | Gate 1 | Technical Feasibility | System uptime | Application and field support uptime. | range | high | Yes | % | 97.4 | 97 | 95 | 80 | 100 | 0.1 |  |  |  |  | MGD PC | [12 empty] | MGD PC | Jan–Mar 2026 | Configuration & setup | Train pilot supervisors on assisted workflow | Ops | Done |  |  | 100 |  |  |  |  | 100%
MGD PC | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek MGD PC, gate ini fokus pada operational efficiency, waste reduction, and quality improvement. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Operational efficiency, waste reduction, and quality improvement. | [6 empty] | MGD PC | Gate 2 | Performance / Effectiveness | Guidance accuracy | Accuracy of field guidance versus target. | range | high | No | % | 86 | 90 | 85 | 60 | 100 | 1 |  |  |  |  | MGD PC | [12 empty] | MGD PC | Jan–Mar 2026 | Pilot proving | Improve guidance accuracy at variable work fronts | Vendor + Ops | Progress |  |  | 0.5 |  |  |  |  | 50%
MGD PC | [14 empty] | MGD PC | Gate 2 | Performance / Effectiveness | Rework reduction | Reduction in repeated work or adjustment. | range | high | No | % | 6 | 8 | 4 | 0 | 20 | 1 |  |  |  |  | MGD PC | [12 empty] | MGD PC | Jan–Mar 2026 | Pilot proving | Monitor user adoption and coaching needs | Supervisor | Progress |  |  | 0.5 |  |  |  |  | 50%
MGD PC | [14 empty] | MGD PC | Gate 2 | Performance / Effectiveness | User acceptance | Supervisor/operator willingness to use the solution. | range | high | No | % | 72 | 80 | 70 | 0 | 100 | 1 |  |  |  |  | MGD PC | [12 empty] | MGD PC | Jan–Mar 2026 | Pilot proving | Review rework reduction evidence by shift | Project Analyst | Plan |  |  | 0 |  |  |  |  | 0%
MGD PC | [14 empty] | MGD PC | Gate 3 | Safety Case & Procedure | Override readiness | Manual fallback and override usability. | select |  | Yes |  | pass | [9 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | Gate 3 | Safety Case & Procedure | Pilot SOP | Approved procedure for assisted/manual operation. | select |  | Yes |  | pass | [9 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | Gate 3 | Safety Case & Procedure | Critical risk closure | Closure of open major safety issues. | range | high | Yes | % | 100 | 100 | 90 | 0 | 100 | 1 |  |  |  |  | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | Gate 4 | Business / Assurance | Cycle benefit | Cycle improvement from assisted guidance. | range | high | No | % | 6 | 8 | 5 | 0 | 20 | 1 |  |  |  |  | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | Gate 4 | Business / Assurance | Waste / rework gain | Reduction in avoidable quality loss. | range | high | No | % | 5 | 7 | 4 | 0 | 20 | 1 |  |  |  |  | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | Gate 4 | Business / Assurance | Scale rationale | Readiness to move beyond proof-of-concept stage. | select |  | No |  | conditional | [9 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC
MGD PC | [14 empty] | MGD PC | [18 empty] | MGD PC | [12 empty] | MGD PC

## Mining Eyes Analytics
Mining Eyes Analytics - PIC Working Sheet
Section ditata ke kanan (side-by-side) agar PIC bebas menambah row per tabel. Input progres hanya di Timeline Tasks (Start Date + Actual %); Period Progress dan Project Progress roll-up otomatis.
Project Summary
Project | Mining Eyes Analytics |  |  | Pilot Area | PAMA BMO2, PAMA GMO, MTN SMO
Subtitle / Context | AI surveillance and analytics pilot where assurance value can be as important as direct cash ROI. |  |  | Support Needed | 5G infrastructure, cloud, surveillance dashboard (HRZ)
Current Phase | Coverage improvement & workflow hardening |  |  | Progress %
Current Period | Apr–Jun 2026 |  |  | Next Milestone | False positive reduction and closure workflow maturity
Need Support (PIC)
Gate Definitions | [14 empty] | Gate Metrics | [18 empty] | Timeline Periods | [12 empty] | Timeline Tasks
Project | Gate | Gate Title | Hard Gate | Gate Definition | Project-specific Explanation | What This Gate Confirms | What PIC Needs to Fill | Original Caption | PIC Status | PIC Notes / Key Findings | Evidence Link / Folder | PIC Owner | Target Close Date | Reviewer Status | Project | Gate | Gate Title | Metric Name | Metric Description | Metric Type | Direction | Critical | Unit | Current Value | Pass Threshold | Conditional Threshold | Min | Max | Step | PIC Current Finding | PIC Evidence / Source | PIC Comment | Metric Status | Project | Current Period | Roadmap Period | Phase | Period Status | Period Explanation | Planned Objective / Outcome | PIC Update Summary | PIC Risks / Dependencies | PIC Owner | Target Date | Reviewer Status | Period Progress % | Project | Roadmap Period | Phase | Task | Original Owner | Original Status | PIC Actual Owner | PIC Start Date | PIC Actual % Input | PIC Progress Note | Evidence Link | Target Date | Dependency / Blocker | Task Progress % (Normalized)
Mining Eyes Analytics | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Mining Eyes Analytics, gate ini fokus pada camera uptime, inference flow, bandwidth, and stream stability. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Camera uptime, inference flow, bandwidth, and stream stability. | [6 empty] | Mining Eyes Analytics | Gate 1 | Technical Feasibility | Camera uptime | Video source availability for analytics. | range | high | No | % | 96.5 | 97 | 95 | 70 | 100 | 0.1 |  |  |  |  | Mining Eyes Analytics | Apr - Jun 2026 | Jan–Mar 2026 | Camera and analytics setup |  | Fase Camera and analytics setup pada periode Jan–Mar 2026 untuk Mining Eyes Analytics. | Deploy camera integration and basic inference flow; Stand up surveillance dashboard and alert feed; Define escalation owners and verification workflow | [6 empty] | Mining Eyes Analytics | Jan - Mar 2026 | Camera and analytics setup | Deploy camera integration and basic inference flow | Vendor | Done |  |  | 1 |  |  |  |  | 100%
Mining Eyes Analytics | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Mining Eyes Analytics, gate ini fokus pada precision, recall, alert usefulness, and missed-event reduction. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Precision, recall, alert usefulness, and missed-event reduction. | [6 empty] | Mining Eyes Analytics | Gate 1 | Technical Feasibility | Inference latency | Speed from event to generated alert. | range | low | No | ms | 220 | 250 | 350 | 50 | 700 | 10 |  |  |  |  | Mining Eyes Analytics | Apr - Jun 2026 | Jan–Mar 2026 | Model and workflow improvement |  | Fase Model and workflow improvement pada periode Apr–Jul 2026 untuk Mining Eyes Analytics. | Reduce false positives at priority use cases; Improve closure discipline and evidence linkage; Strengthen coverage in unstable network areas | [6 empty] | Mining Eyes Analytics | Jan - Mar 2026 | Camera and analytics setup | Stand up surveillance dashboard and alert feed | IT / Analytics | Done |  |  | 1 |  |  |  |  | 100%
Mining Eyes Analytics | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Mining Eyes Analytics, gate ini fokus pada alert escalation, role clarity, verification workflow, and evidence retention. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Alert escalation, role clarity, verification workflow, and evidence retention. | [6 empty] | Mining Eyes Analytics | Gate 1 | Technical Feasibility | Coverage stability | Consistency of effective area coverage. | range | high | Yes | % | 82 | 85 | 75 | 0 | 100 | 1 |  |  |  |  | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics | Jan - Mar 2026 | Camera and analytics setup | Define escalation owners and verification workflow | OHS | Done |  |  | 1 |  |  |  |  | 100%
Mining Eyes Analytics | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Mining Eyes Analytics, gate ini fokus pada monitoring coverage, assurance value, and reduction of missed critical events. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Monitoring coverage, assurance value, and reduction of missed critical events. | [6 empty] | Mining Eyes Analytics | Gate 2 | Performance / Effectiveness | Precision | Alert correctness rate. | range | high | No | % | 84 | 90 | 80 | 50 | 100 | 1 |  |  |  |  | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics | Jan - Mar 2026 | Model and workflow improvement | Reduce false positives at priority use cases | AI Team | Progress |  |  | 0.5 |  |  |  |  | 50%
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | Gate 2 | Performance / Effectiveness | Recall | Ability to capture true events. | range | high | No | % | 78 | 85 | 75 | 50 | 100 | 1 |  |  |  |  | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics | Jan - Mar 2026 | Model and workflow improvement | Improve closure discipline and evidence linkage | Ops + OHS | Progress |  |  | 0.5 |  |  |  |  | 50%
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | Gate 2 | Performance / Effectiveness | False positive rate | Lower rate reduces alert fatigue. | range | low | No | /hr | 0.45 | 0.25 | 0.45 | 0 | 1 | 0.01 |  |  |  |  | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics | Jan - Mar 2026 | Model and workflow improvement | Strengthen coverage in unstable network areas | IT | Risk |  |  | 0.25 |  |  |  |  | 25%
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | Gate 3 | Safety Case & Procedure | Escalation SOP | Owner and response flow for incoming alerts. | select |  | Yes |  | pass | [9 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | Gate 3 | Safety Case & Procedure | Audit trail | Evidence trace and alert history reviewability. | select |  | Yes |  | pass | [9 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | Gate 3 | Safety Case & Procedure | Closure workflow | Quality of action closure discipline. | range | high | No | % | 72 | 80 | 70 | 0 | 100 | 1 |  |  |  |  | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | Gate 4 | Business / Assurance | Coverage uplift | Increase in monitored area or observation capability. | range | high | No | % | 31 | 25 | 15 | 0 | 50 | 1 |  |  |  |  | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | Gate 4 | Business / Assurance | Manual review reduction | Potential reduction in CCTV review effort. | range | high | No | % | 18 | 20 | 10 | 0 | 40 | 1 |  |  |  |  | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | Gate 4 | Business / Assurance | Assurance case | Strength of visibility and auditability justification. | select |  | No |  | pass | [9 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics
Mining Eyes Analytics | [14 empty] | Mining Eyes Analytics | [18 empty] | Mining Eyes Analytics | [12 empty] | Mining Eyes Analytics

## Remote Pump
Remote Pump - PIC Working Sheet
Section ditata ke kanan (side-by-side) agar PIC bebas menambah row per tabel. Input progres hanya di Timeline Tasks (Start Date + Actual %); Period Progress dan Project Progress roll-up otomatis.
Project Summary
Project | Remote Pump |  |  | Pilot Area | BC SMO - ACI, BC BMO1 - PMO
Subtitle / Context | Remote operation pilot emphasizing interlock integrity, fail-safe response, and exposure reduction in pump areas. |  |  | Support Needed | 5G / telemetry network, PLC integration, remote command governance
Current Phase | Functional validation & availability proving |  |  | Progress %
Current Period | Apr–Jun 2026 |  |  | Next Milestone | Interlock sign-off and rollout readiness
Need Support (PIC)
Gate Definitions | [14 empty] | Gate Metrics | [18 empty] | Timeline Periods | [12 empty] | Timeline Tasks
Project | Gate | Gate Title | Hard Gate | Gate Definition | Project-specific Explanation | What This Gate Confirms | What PIC Needs to Fill | Original Caption | PIC Status | PIC Notes / Key Findings | Evidence Link / Folder | PIC Owner | Target Close Date | Reviewer Status | Project | Gate | Gate Title | Metric Name | Metric Description | Metric Type | Direction | Critical | Unit | Current Value | Pass Threshold | Conditional Threshold | Min | Max | Step | PIC Current Finding | PIC Evidence / Source | PIC Comment | Metric Status | Project | Current Period | Roadmap Period | Phase | Period Status | Period Explanation | Planned Objective / Outcome | PIC Update Summary | PIC Risks / Dependencies | PIC Owner | Target Date | Reviewer Status | Period Progress % | Project | Roadmap Period | Phase | Task | Original Owner | Original Status | PIC Actual Owner | PIC Start Date | PIC Actual % Input | PIC Progress Note | Evidence Link | Target Date | Dependency / Blocker | Task Progress % (Normalized)
Remote Pump | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Remote Pump, gate ini fokus pada command success, telemetry completeness, and communication stability. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Command success, telemetry completeness, and communication stability. | [6 empty] | Remote Pump | Gate 1 | Technical Feasibility | Command success rate | Success of issued remote command. | range | high | Yes | % | 98.8 | 98 | 95 | 80 | 100 | 0.1 |  |  |  |  | Remote Pump | Apr - Jun 2026 | Jan - Mar 2026 | Remote control commissioning |  | Fase Remote control commissioning pada periode Jan–Mar 2026 untuk Remote Pump. | Commission telemetry and command loop; Validate remote signal reliability; Prepare pump isolation and takeover workflow | [6 empty] | Remote Pump | Jan–Mar 2026 | Remote control commissioning | Commission telemetry and command loop | Automation | Done |  |  | 1 |  |  |  |  | 100%
Remote Pump | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Remote Pump, gate ini fokus pada availability, remote-control reliability, and downtime impact. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Availability, remote-control reliability, and downtime impact. | [6 empty] | Remote Pump | Gate 1 | Technical Feasibility | Telemetry completeness | Availability of remote feedback and audit data. | range | high | No | % | 97 | 95 | 90 | 70 | 100 | 1 |  |  |  |  | Remote Pump | Apr - Jun 2026 | Jan - Mar 2026 | Operational pilot and fail-safe proving |  | Fase Operational pilot and fail-safe proving pada periode Apr–Jul 2026 untuk Remote Pump. | Complete fail-safe loss-of-signal scenarios; Track downtime reduction against baseline; Document local override discipline by area | [6 empty] | Remote Pump | Jan–Mar 2026 | Remote control commissioning | Validate remote signal reliability | IT / Vendor | Done |  |  | 1 |  |  |  |  | 100%
Remote Pump | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Remote Pump, gate ini fokus pada interlock, local override, fail-safe loss-of-signal logic. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Interlock, local override, fail-safe loss-of-signal logic. | [6 empty] | Remote Pump | Gate 1 | Technical Feasibility | Communication uptime | Reliability of communication channel. | range | high | Yes | % | 99 | 98 | 96 | 80 | 100 | 0.1 |  |  |  |  | Remote Pump | [12 empty] | Remote Pump | Jan–Mar 2026 | Remote control commissioning | Prepare pump isolation and takeover workflow | Maintenance | Done |  |  | 1 |  |  |  |  | 100%
Remote Pump | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Remote Pump, gate ini fokus pada travel exposure reduction, avoided delays, and operating value. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Travel exposure reduction, avoided delays, and operating value. | [6 empty] | Remote Pump | Gate 2 | Performance / Effectiveness | Remote availability | Ability to operate remotely when needed. | range | high | No | % | 91 | 90 | 85 | 50 | 100 | 1 |  |  |  |  | Remote Pump | [12 empty] | Remote Pump | Apr–Jul 2026 | Operational pilot and fail-safe proving | Complete fail-safe loss-of-signal scenarios | Automation + OHS | Progress |  |  | 0.5 |  |  |  |  | 50%
Remote Pump | [14 empty] | Remote Pump | Gate 2 | Performance / Effectiveness | Response latency | Control response time under operating condition. | range | low | No | ms | 180 | 200 | 250 | 50 | 400 | 5 |  |  |  |  | Remote Pump | [12 empty] | Remote Pump | Apr–Jul 2026 | Operational pilot and fail-safe proving | Track downtime reduction against baseline | Project Analyst | Progress |  |  | 0.5 |  |  |  |  | 50%
Remote Pump | [14 empty] | Remote Pump | Gate 2 | Performance / Effectiveness | Downtime reduction | Reduction in event-driven downtime. | range | high | No | % | 11 | 10 | 5 | 0 | 30 | 1 |  |  |  |  | Remote Pump | [12 empty] | Remote Pump | Apr–Jul 2026 | Operational pilot and fail-safe proving | Document local override discipline by area | Maintenance | Plan |  |  | 0 |  |  |  |  | 0%
Remote Pump | [14 empty] | Remote Pump | Gate 3 | Safety Case & Procedure | Safety interlock | Integrity of remote command permissive chain. | select |  | Yes |  | pass | [9 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | Gate 3 | Safety Case & Procedure | Loss-of-signal fail-safe | Safe fallback when signal is lost. | select |  | Yes |  | pass | [9 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | Gate 3 | Safety Case & Procedure | Isolation procedure | LOTO and local takeover procedure readiness. | select |  | Yes |  | pass | [9 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | Gate 4 | Business / Assurance | Travel exposure reduction | Reduction in personnel movement to pump area. | range | high | No | % | 18 | 15 | 8 | 0 | 40 | 1 |  |  |  |  | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | Gate 4 | Business / Assurance | Delay prevention | Avoided delay from remote intervention. | range | high | No | % | 11 | 10 | 5 | 0 | 20 | 1 |  |  |  |  | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | Gate 4 | Business / Assurance | Economic case | Scale case from avoided loss and assurance benefit. | select |  | No |  | pass | [9 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump
Remote Pump | [14 empty] | Remote Pump | [18 empty] | Remote Pump | [12 empty] | Remote Pump

## Remote Dozer
Remote Dozer - PIC Working Sheet
Section ditata ke kanan (side-by-side) agar PIC bebas menambah row per tabel. Input progres hanya di Timeline Tasks (Start Date + Actual %); Period Progress dan Project Progress roll-up otomatis.
Project Summary
Project | Remote Dozer |  |  | Pilot Area | Kalimantan OB Disposal
Subtitle / Context | Remote dozer pilot with strong linkage between technical readiness, safe remote operation, and direct economical value from fuel and efficiency improvement. |  |  | Support Needed | 5G network, remote control station, video telemetry, autonomous zone & dashboard
Current Phase | Integrated readiness and economic proving |  |  | Progress % | 75%
Current Period | Apr–Jun 2026 |  |  | Next Milestone | Technical + economic pack for scale-up decision
Need Support (PIC)
Gate Definitions | [14 empty] | Gate Metrics | [18 empty] | Timeline Periods | [12 empty] | Timeline Tasks
Project | Gate | Gate Title | Hard Gate | Gate Definition | Project-specific Explanation | What This Gate Confirms | What PIC Needs to Fill | Original Caption | PIC Status | PIC Notes / Key Findings | Evidence Link / Folder | PIC Owner | Target Close Date | Reviewer Status | Project | Gate | Gate Title | Metric Name | Metric Description | Metric Type | Direction | Critical | Unit | Current Value | Pass Threshold | Conditional Threshold | Min | Max | Step | PIC Current Finding | PIC Evidence / Source | PIC Comment | Metric Status | Project | Current Period | Roadmap Period | Phase | Period Status | Period Explanation | Planned Objective / Outcome | PIC Update Summary | PIC Risks / Dependencies | PIC Owner | Target Date | Reviewer Status | Period Progress % | Project | Roadmap Period | Phase | Task | Original Owner | Original Status | PIC Actual Owner | PIC Start Date | PIC Actual % Input | PIC Progress Note | Evidence Link | Target Date | Dependency / Blocker | Task Progress % (Normalized)
Remote Dozer | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Remote Dozer, gate ini fokus pada network readiness, command latency, and telemetry stability for remote dozing. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Network readiness, command latency, and telemetry stability for remote dozing. | [6 empty] | Remote Dozer | Gate 1 | Technical Feasibility | Network uptime | Availability of network used for remote dozer control. | range | high | Yes | % | 99 | 98 | 96 | 80 | 100 | 0.1 |  |  |  |  | Remote Dozer | Apr - Jun 2026 | Jan - Mar 2026 | Remote system setup | Done | Fase Remote system setup pada periode Jan–Mar 2026 untuk Remote Dozer. | Complete network and control station setup; Define remote zone boundary and procedure | [5 empty] | 100% | Remote Dozer | Jan - Mar 2026 | Remote system setup | Complete network and control station setup | Automation | Done |  |  | 1 |  |  |  |  | 100%
Remote Dozer | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Remote Dozer, gate ini fokus pada distance reduction, remote availability, and fuel-saving effectiveness. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Distance reduction, remote availability, and fuel-saving effectiveness. | [6 empty] | Remote Dozer | Gate 1 | Technical Feasibility | Control latency | Round-trip command latency during remote operation. | range | low | Yes | ms | 170 | 200 | 250 | 50 | 400 | 5 |  |  |  |  | Remote Dozer | Apr - Jun 2026 | Apr - Jun 2026 | Pilot run and economic proof | Progress | Fase Pilot run and economic proof pada periode Apr–Aug 2026 untuk Remote Dozer. | Track dozing distance reduction and remote availability; Refresh payback and ROI assumption model | [5 empty] | 50% | Remote Dozer | Jan - Mar 2026 | Remote system setup | Define remote zone boundary and procedure | OHS | Done |  |  | 1 |  |  |  |  | 100%
Remote Dozer | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Remote Dozer, gate ini fokus pada emergency stop, fail-safe logic, zone control, and remote handover readiness. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Emergency stop, fail-safe logic, zone control, and remote handover readiness. | [6 empty] | Remote Dozer | Gate 2 | Performance / Effectiveness | Dozing distance reduction | Reduction in average push distance versus conventional operation. | range | high | No | % | 75 | 60 | 40 | 0 | 100 | 1 |  |  |  |  | Remote Dozer | [12 empty] | Remote Dozer | Apr - Jun 2026 | Pilot run and economic proof | Track dozing distance reduction and remote availability | Ops | Progress |  |  | 0.5 |  |  |  |  | 50%
Remote Dozer | Gate 4 | Business / Economical Pass | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Remote Dozer, gate ini fokus pada net saving, payback, and long-term roi from remote dozer deployment. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Net saving, payback, and long-term ROI from remote dozer deployment. | [6 empty] | Remote Dozer | Gate 2 | Performance / Effectiveness | Remote operating availability | Percentage of planned operating time executed in remote mode. | range | high | No | % | 91 | 85 | 75 | 40 | 100 | 1 |  |  |  |  | Remote Dozer | [12 empty] | Remote Dozer | Apr - Jun 2026 | Pilot run and economic proof | Refresh payback and ROI assumption model | Project Analyst | Progress |  |  | 0.5 |  |  |  |  | 50%
Remote Dozer | [14 empty] | Remote Dozer | Gate 3 | Safety Case & Procedure | Emergency stop readiness | Remote and local emergency stop function. | select |  | Yes |  | pass | [9 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | Gate 3 | Safety Case & Procedure | Loss-of-signal fail-safe | Machine response when communication is interrupted. | select |  | Yes |  | pass | [9 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | Gate 4 | Business / Economical Pass | Net saving / month | Monthly net saving after fuel saving and maintenance impact. | range | high | No | M IDR | 165 | 100 | 40 | -100 | 300 | 1 |  |  |  |  | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | Gate 4 | Business / Economical Pass | Simple payback | Capital recovery period. Lower is better. | range | low | No | mo | 21 | 36 | 60 | 1 | 120 | 1 |  |  |  |  | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | Gate 4 | Business / Economical Pass | 5-year ROI | Return on investment over five years after CAPEX recovery. | range | high | No | % | 183 | 50 | 0 | -100 | 400 | 1 |  |  |  |  | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer
Remote Dozer | [14 empty] | Remote Dozer | [18 empty] | Remote Dozer | [12 empty] | Remote Dozer

## Hauling Fleet Management
Hauling Fleet Management - PIC Working Sheet
Section ditata ke kanan (side-by-side) agar PIC bebas menambah row per tabel. Input progres hanya di Timeline Tasks (Start Date + Actual %); Period Progress dan Project Progress roll-up otomatis.
Project Summary
Project | Hauling Fleet Management |  |  | Pilot Area | MTL BMO1
Subtitle / Context | Optimization pilot where dispatch quality, queue reduction, and utilization improvement drive the business case. |  |  | Support Needed | Fleet data pipeline, dispatch integration, performance dashboard
Current Phase | Optimization scaling |  |  | Progress %
Current Period | Apr–Jun 2026 |  |  | Next Milestone | Portfolio-scale dispatch recommendation
Need Support (PIC)
Gate Definitions | [14 empty] | Gate Metrics | [18 empty] | Timeline Periods | [12 empty] | Timeline Tasks
Project | Gate | Gate Title | Hard Gate | Gate Definition | Project-specific Explanation | What This Gate Confirms | What PIC Needs to Fill | Original Caption | PIC Status | PIC Notes / Key Findings | Evidence Link / Folder | PIC Owner | Target Close Date | Reviewer Status | Project | Gate | Gate Title | Metric Name | Metric Description | Metric Type | Direction | Critical | Unit | Current Value | Pass Threshold | Conditional Threshold | Min | Max | Step | PIC Current Finding | PIC Evidence / Source | PIC Comment | Metric Status | Project | Current Period | Roadmap Period | Phase | Period Status | Period Explanation | Planned Objective / Outcome | PIC Update Summary | PIC Risks / Dependencies | PIC Owner | Target Date | Reviewer Status | Period Progress % | Project | Roadmap Period | Phase | Task | Original Owner | Original Status | PIC Actual Owner | PIC Start Date | PIC Actual % Input | PIC Progress Note | Evidence Link | Target Date | Dependency / Blocker | Task Progress % (Normalized)
Hauling Fleet Management | Gate 1 | Technical Feasibility | Yes | Menilai kelayakan teknis dasar solusi sebelum pilot dilanjutkan atau diperluas. | Untuk proyek Hauling Fleet Management, gate ini fokus pada data ingestion, gps continuity, dashboard uptime, and integration. | Kesiapan infrastruktur, integrasi sistem, kualitas data/sinyal, stabilitas teknis, uptime, latency, dan reliability. | Lengkapi evidence hasil uji teknis, gap teknis terbuka, mitigasi, dan rekomendasi readiness. | Data ingestion, GPS continuity, dashboard uptime, and integration. | [6 empty] | Hauling Fleet Management | Gate 1 | Technical Feasibility | Data ingestion | Consistency of live fleet data ingestion. | range | high | No | % | 97 | 95 | 90 | 70 | 100 | 1 |  |  |  |  | Hauling Fleet Management | Apr - Jun 2026 | Jan–Mar 2026 | Data and dashboard stabilization |  | Fase Data and dashboard stabilization pada periode Jan–Mar 2026 untuk Hauling Fleet Management. | Stabilize fleet data ingestion pipeline; Launch dispatcher dashboard and KPI baseline; Validate refresh cycle for operational use | [6 empty] | Hauling Fleet Management | Jan - Mar 2026 | Data and dashboard stabilization | Stabilize fleet data ingestion pipeline | Data Eng | Done |  |  | 1 |  |  |  |  | 100%
Hauling Fleet Management | Gate 2 | Performance / Effectiveness | No | Membuktikan bahwa solusi memberi hasil operasional yang relevan dengan tujuan proyek. | Untuk proyek Hauling Fleet Management, gate ini fokus pada queue time, idle time, and cycle optimization effectiveness. | Akurasi, efektivitas, availability, pengurangan loss, peningkatan produktivitas, atau manfaat performa lain sesuai use case. | Lengkapi baseline vs actual, hasil pilot, variasi performa, akar masalah, dan action plan. | Queue time, idle time, and cycle optimization effectiveness. | [6 empty] | Hauling Fleet Management | Gate 1 | Technical Feasibility | Dashboard uptime | Operational dashboard availability. | range | high | Yes | % | 99.2 | 98 | 96 | 80 | 100 | 0.1 |  |  |  |  | Hauling Fleet Management | Apr - Jun 2026 | Jan–Mar 2026 | Optimization proving |  | Fase Optimization proving pada periode Apr–Aug 2026 untuk Hauling Fleet Management. | Track queue and idle reduction by shift; Improve user adoption across supervisors; Lock fuel and utilization uplift evidence | [6 empty] | Hauling Fleet Management | Jan - Mar 2026 | Data and dashboard stabilization | Launch dispatcher dashboard and KPI baseline | Analytics | Done |  |  | 1 |  |  |  |  | 100%
Hauling Fleet Management | Gate 3 | Safety Case & Procedure | Yes | Memastikan proyek aman dijalankan dan governance operasionalnya siap. | Untuk proyek Hauling Fleet Management, gate ini fokus pada override, rule compliance, and alignment with road safety logic. | SOP, override, fail-safe, escalation path, audit trail, handover, interlock, dan penutupan risiko kritikal. | Lengkapi status SOP, hasil simulasi/drill, kontrol keselamatan, approval safety, dan gap residual. | Override, rule compliance, and alignment with road safety logic. | [6 empty] | Hauling Fleet Management | Gate 1 | Technical Feasibility | Refresh cycle | Minutes needed for usable data refresh. | range | low | No | min | 5 | 10 | 20 | 1 | 60 | 1 |  |  |  |  | Hauling Fleet Management | [12 empty] | Hauling Fleet Management | Jan - Mar 2026 | Data and dashboard stabilization | Validate refresh cycle for operational use | Ops Control | Done |  |  | 1 |  |  |  |  | 100%
Hauling Fleet Management | Gate 4 | Business / Assurance | No | Menilai kelayakan scale-up dari sisi bisnis, assurance, atau keekonomian. | Untuk proyek Hauling Fleet Management, gate ini fokus pada fuel efficiency, utilization, and dispatch-led value creation. | Nilai bisnis, reduction of exposure/loss, assurance value, economic case, payback, ROI, atau justification deployment lebih luas. | Lengkapi manfaat terukur, asumsi bisnis/ekonomi, alasan scale-up, risiko bisnis, dan rekomendasi akhir. | Fuel efficiency, utilization, and dispatch-led value creation. | [6 empty] | Hauling Fleet Management | Gate 2 | Performance / Effectiveness | Queue time reduction | Reduction in waiting queue for loading/unloading. | range | high | No | % | 14 | 10 | 5 | 0 | 30 | 1 |  |  |  |  | Hauling Fleet Management | [12 empty] | Hauling Fleet Management | Jan - Mar 2026 | Optimization proving | Track queue and idle reduction by shift | Dispatcher | Progress |  |  | 0.5 |  |  |  |  | 50%
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | Gate 2 | Performance / Effectiveness | Idle reduction | Reduction in idle or non-productive unit time. | range | high | No | % | 10 | 8 | 4 | 0 | 20 | 1 |  |  |  |  | Hauling Fleet Management | [12 empty] | Hauling Fleet Management | Jan - Mar 2026 | Optimization proving | Improve user adoption across supervisors | Ops | Progress |  |  | 0.5 |  |  |  |  | 50%
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | Gate 2 | Performance / Effectiveness | User adoption | Dispatcher and supervisor usage level. | range | high | No | % | 89 | 85 | 75 | 0 | 100 | 1 |  |  |  |  | Hauling Fleet Management | [12 empty] | Hauling Fleet Management | Jan - Mar 2026 | Optimization proving | Lock fuel and utilization uplift evidence | Project Analyst | Plan |  |  | 0 |  |  |  |  | 0%
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | Gate 3 | Safety Case & Procedure | Safety conflict check | No contradiction with road-rule protections. | select |  | Yes |  | pass | [9 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | Gate 3 | Safety Case & Procedure | Audit trail | Decision traceability and reviewability. | select |  | No |  | pass | [9 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | Gate 3 | Safety Case & Procedure | Escalation path | Manual override and escalation remain available. | select |  | Yes |  | pass | [9 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | Gate 4 | Business / Assurance | Fuel benefit | Improvement in fuel-related operating value. | range | high | No | % | 6 | 5 | 2 | 0 | 15 | 1 |  |  |  |  | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | Gate 4 | Business / Assurance | Utilization uplift | Increase in productive fleet use. | range | high | No | % | 9 | 7 | 4 | 0 | 20 | 1 |  |  |  |  | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | Gate 4 | Business / Assurance | Scale economics | Strength of economic case for wider deployment. | select |  | No |  | pass | [9 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management
Hauling Fleet Management | [14 empty] | Hauling Fleet Management | [18 empty] | Hauling Fleet Management | [12 empty] | Hauling Fleet Management

## Dropdown_Lists
Metric Type | Direction | Critical | Unit | Gate/Metric Status | Reviewer Status | Legacy Timeline Status (not used for task roll-up) | Periode Roadmap
range | high | Yes | % | Pass | Open | Done | Jan - Mar 2026
select | low | No | ms | Conditional | In Review | Progress | Apr - Jun 2026
| n/a |  | min | Fail | Closed | Risk | Jul- Sept 2026
|  |  | pts | Need Check |  | Plan | Oct - Dec 2026
|  |  | /hr | Not Started |  | Blocked
M IDR
mo